## Summary
QA Status |  | Dev Team Status
Row Labels | Count of QA Status | Row Labels | Count of Dev Status
Not Resolved | 10 | Closed | 3
(blank) |  | Open | 11
Pending | 1 | (blank)
Done | 3 | - | 1
- | 1 | Grand Total | 15
Grand Total | 15

## LMS ISSUES
Ticket No | Date | Issue / Bug | Product | File Name/ Attachments | Major/Minor | Priority | Effort | Resource | Raised by | Dev Status | QA Status | Type | Re-Open Date | Closed Date | Comments by QA | Comments by Dev. Team | User FeedBack
T-1001 | 2019-02-08 | SIGN OUT PROCESS | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality | 2019-02-18 |  | OK
T-1002 | 2019-02-08 | Activation Through Email | LMS | BU Email: (RE: LMS on port 80 with Alias) | Major | High |  |  | QA | Closed | Done | Functionality |  | 2019-02-11 | OK
T-1003 | 2019-02-08 | Educational Document not editable or deleted | LMS | BU Email: (RE: LMS on port 80 with Alias) | Major | High |  |  | QA | - | - | Functionality | - | - |  | New Requirement, wasn’t implement by TRG
T-1004 | 2019-02-08 | Error appearing User In-Active issue | LMS | BU Email: (RE: LMS on port 80 with Alias) | Major | High |  |  | QA | Closed | Done | Functionality |  | 2019-02-11 | OK
T-1005 | 2019-02-08 | Excel file when extracted | LMS | BU Email: (RE: LMS on port 80 with Alias) | Major | High |  |  | QA | Open | Pending | Functionality | - | - |  | Working on it, will revert you by Monday first half, need to change the functionality as of now excel file is generating from JavaScript which has the limitation of 1000 records.
T-1006 | 2019-02-08 | Registration | LMS | BU Email: (RE: LMS on port 80 with Alias) | Major | High |  |  | QA | Closed | DOne | Functionality |  | 2019-02-11 | OK
T-1007 | 2019-02-18 | Forget Password | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality |  |  | Enter Wrong email Shows message box. That have no message. Title and logo is wrong, it should be warning and logo should be warning logo, • If I have enter the correct email then received an email with reset password link, After Opening the reset link I’ve enter the wrong values it shows message box that shows no message
T-1008 | 2019-02-18 | Signup | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality |  |  | Fill the signgup form and received Email/ SMS , Enter wrong values in the form and received below message that is wrong. Please show appropriate message logo and title.
T-1009 | 2019-02-18 | Dashboard | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality | 2019-02-19 |  | On Clicking to the highlighted Picture Application got crashed. As shown in the attached document, Trainer Dashboard not showing anything.
T-1010 | 2019-02-18 | Menu Item / Side Bar: | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality | 2019-02-19 |  | There is inconsistency in the side bar as shown in the below SC.
T-1011 | 2019-02-18 | My Profile - User Profile Edit | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality |  |  | This is no Error if this is the warning if I did not fill the complete form. Shows the appropriate message. On Edit Rights are not showing. Deactivation, Blacklist and send notification are not working. - There is no validation working on country dropdown, Although validation messages are inappropriate. Date Of Birth save current date By default cannot intimate or validate on saving. - Clicking on Add More for Educational document. IT shows nothing because of cache issue. and it is not validate on saving. - Educational Qualification Button is not working and on clicking of document, Application got crashed.
T-1012 | 2019-02-18 | Basic Traning | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality |  |  | Take Quiz On clicking the label take quiz I got this message, it is not error and logo is not appropriate. (I was not redirect to quiz page because of educational document is not saved yet but on saving the profile validation is not working for this education document section) . - Quiz Options selection issue.
T-1013 | 2019-02-18 | Report Card | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality |  |  | Image is not showing.
T-1014 | 2019-02-18 | Forum | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality |  |  | Validation Messages, - Not showing saved discussion.
T-1015 | 2019-02-18 | Cache Issues | LMS | BU Email: (RE: LMS - UAT Link) | Major | High |  |  | QA | Open | Not Resolved | Functionality

## MOBILE APP ISSUES
App Name | Issue Name | Issue Detail | Status | Report Date | Resolve Date
TPL Insurance iOS App | Home Ins - Name Limit | In Home Insurance section , on first screen form the name field limit to be increased | Resolved | 2019-01-11 | 2019-01-12